## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
I get overloaded with work from my capstone | 20 | 13 | 260 | 2021-04-01 | Mitigated | M | Work Ahead to account for one week of lost time
I miss the deadline for the project | 8 | 20 | 160 | 2021-04-01 | Mitigated | M | Make a schedule and stick to it
I get sick | 3 | 40 | 120 | 2021-04-01 | Mitigated | M | know the instructor has extension and ask if sick
Github Crashes and I lose all my work | 1 | 100 | 100 | 2021-04-01 |  | A | Very unlikly to happen
My Computer Dies | 2 | 40 | 80 | 2021-04-01 |  | O | Buy a new computer if it happens
Simplicity has an update that bugs my project | 20 | 3 | 60 | 2021-04-01 |  | A | Do no update until after the project is finished
My Pearl Gecko Board stops working | 3 | 20 | 60 | 2021-04-01 |  | O | Test it. If mine not working, contact instructor
My charger breaks | 2 | 20 | 40 | 2021-04-01 | Resolved | R | Have a second charger
My internet goes down | 40 | 1 | 40 | 2021-04-01 |  | O | Wait a few minutes and it should be back up

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100